## Project Planner
KentSoft Gantt Chart
Actual Duration
ACTIVITY | PLAN START | PLAN DURATION (days) | ACTUAL START | ACTUAL DURATION (days) | PERCENT COMPLETE |  | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51
Set up Microsoft Word Document of meeting template | 2020-01-21 | 3 | 2020-01-22 | 2 | 100% | bar: PERIODS 2 to PERIODS 3
Set up Gitlab | 2020-01-21 | 3 | 2020-01-21 | 3 | 100%
Create chart of meeting hours | 2020-01-21 | 3 | 2020-01-21 | 3 | 100%
Create company name | 2020-01-21 | 1 | 2020-01-21 | 1 | 100%
Create company logo | 2020-01-23 | 6 | 2020-01-28 | 1 | 100%
Book room for next meeting | 2020-01-28 | 1 | 2020-01-28 | 1 | 100% | bar: PERIODS 5
Word style document | 2020-01-29 | 1 | 2020-01-29 | 1 | 100%
Review document | 2020-01-29 | 3 | 2020-01-30 | 2 | 100%
Code style documeny | 2020-01-29 | 3 | 2020-01-31 | 1 | 100%
Software test plan | 2020-01-29 | 1 | 2020-01-29 | 5 | 100%
Check UML diagrams against use case descriptions | 2020-01-30 | 1 | 2020-01-30 | 1 | 100%
Email Miles regarding queries | 2020-01-30 | 1 | 2020-01-30 | 1 | 100%
Project management document | 2020-01-30 | 2 | 2020-01-31 | 1 | 100%
QA document | 2020-01-30 | 3 | 2020-02-01 | 3 | 100%
Re-email Miles due to not including feedback in email by mistake | 2020-01-31 | 1 | 2020-01-31 | 1 | 100%
Update chart with meeting hours | 2020-01-31 | 1 | 2020-01-31 | 1 | 100%
Reorganise Trello | 2020-01-31 | 1 | 2020-01-31 | 1 | 100%
Criteria Document | 2020-01-31 | 3 | 2020-02-02 | 3 | 100%
Go through documents to ensure font and sizing conforms to guidelines | 2020-01-31 | 3 | 2020-02-02 | 3 | 100%
Start Developing the model in UML from revises use cases / descriptions and from Miles responses | 2020-01-31 | 3 | 2020-02-02 | 3 | 100%